## Overall
Phase | Description | Done | Date Completed
0 | PreProduction | y | 18/11/2016
1 | User Interaction and Movement | N
2 | Scoring and Entity interaction | N
3 | HUD and Game Flow | N
4 | Polish | N
5 | Final Testing | N

## Phase 1
Phase 1 : User Interaction and Player Movement
Task | Subtask | Priority | Done | Notes
User input |  | 1 | y
User input | Controller inputs | 1 | y | Can we get Inputs from The controller
Game Manager |  | 1 | N | Create a game manager that will instantiate the players and game mode
Game Manager | Game mode | 1 | N | Create the endless game mode
Player setup |  | 2 | y | Set up the player prefab for initial testing
Player movement |  | 2 | y | Can we move around the environment excluding boost and dodge
Player setup | Camera | 2 | y | Position the camera to above the player
Player setup | Player Identifier sfx | 2 | N | Particle system for identifying the Player's Ship
Player setup | Placeholder Ship | 2 | y | Get a ship to use for inital testing of movement
Environment setup |  | 2 | y
Environment setup | Placeholder enviro | 2 | y | Set up a simple environemnt for moving around during testing
Dodge |  | 3 | y
Dodge | Invuln | 3 | y | Are we invulnerable during dodging
Dodge | Roll Dodge | 3 | y | Can we roll to a chosen side properly
Dodge | Flip Dodge | 3 | y | Can we Flip on the spot
Boost |  | 3 | y
Boost | Invuln | 3 | y | Are we invulnerable for the boost duration
Boost | Movement | 3 | y | move the player in the direction they are facing
Prefab Creation |  | 4 | y | Create prefabs for all visual objects, empty game objects that can hold an object of that type
Prefab Creation | AbsMissile | 4 | y | Create Missile Prefab
Prefab Creation | AbsPlayer | 4 | y | Create Player Prefab
Prefab Creation | AbsShip | 4 | y | Create Ship prefab
Prefab Creation | AbsBullet | 4 | y | Create Bullet Prefab
Prefab Creation | Pickup | 5 | n | CreatePickup Prefab

## Phase 2
Phase 2 : Scoring and Entity Interaction
Task | Subtask | Priority | Done | Notes
Shoot Bullet |  | 1 | y | Fire a number of bullets
Shoot Bullet | Create Bullet Visual | 1 | y | Create the visual representation of each of the types of bullets
Shoot Bullet | Instantiate | 1 | y
Shoot Bullet | Movement | 1 | y | Make them move in a straight line in the correct direction
Shoot Missile |  | 1 | y | Fire a number of missiles
Shoot Missile | Create Missile Visual | 1 | y | Create the visual representation of each of the types of missile
Shoot Missile | Instantiate | 1 | y
Shoot Missile | Choose Target | 1 | y | Follow algorithm in the use case specifications
Shoot Missile | Calc Target Vector | 1 | y
Shoot Missile | Move | 1 | y
AI Player |  | 2 | y | Add an ai player to interact with
AI Player | Chase player | 2 | N | move towards the player and
AI Player | Shoot when in range | 2 | y | when in a certain range fire
AI Player | Change Playstyle | 6 | y | set up rules for each of the playstyles
Take Damage |  | 3 | N
Take Damage | Hit Visual | 3 | N | find or create a particle effect to represent the hitspark
Take Damage | Collision Checking | 3 | y | Check for collisions and apply damage
Take Damage | Death Visual | 3 | N | create or find a visual for ship death
Add Scrap |  | 3 | y | If 0 hp add scrap/exp
Upgrade |  | 4 | N
Upgrade | Upgrade tree | 4 | N | Visuals and GUI
Upgrade | Upgrades | 4 | N | code for each fo the upgrades
Pickups |  | 5 | N
Pickups | Collisions | 5 | N | Can the palyer get pickups
Pickups | Duration | 5 | N | do the pickups stop after the correct duration, can more than one be picked up?

## Phase 3
Phase 3 : HUD, Audio and Game Flow
Task | Subtask | Priority | Done | Notes
Player HUD |  | 1 | N
Player HUD | HUD overlay | 1 | y
Player HUD | Game Time | 1 | n
Player HUD | Health Bar | 1 | y
Player HUD | Shield Bar | 1 | y
Player HUD | Stat Area | 1 | n
Player HUD | Current Ship | 1 | n
Player HUD | Cooldowns | 1 | y
Player HUD | Exp/Scrap Bar | 1 | y
Menu System |  | 2 | N
Menu System | Title | 2 | N
Menu System | Main | 2 | N
Menu System | Mode Select | 2 | N
Menu System | Pause | 2 | N
Menu System | Game Over | 2 | N
Menu System | Upgrade screen | 2 | N
Audio |  | 3 | N
Audio | Music | 3 | N
Audio | Shoot Bullet | 3 | y
Audio | Shoot Missile | 3 | y
Audio | Hit | 3 | y | y
Audio | Explosion | 3 | y
Audio | Ship Movement | 3 | y
Audio | Pick up Pickup | 3 | N
Audio | Pickup Duration | 3 | N
Audio | Boost | 3 | y
Audio | Flip Dodge | 3 | y
Audio | Roll Dodge | 3 | y
Audio | Level Up | 3 | N
Audio | Pause | 4
Audio | Open Upgrade screen | 4 | N
Audio | Menu Selection | 4 | N
Audio | Menu Movement | 4 | N

## Phase 4
Phase 4 : Polish
Task | Subtask | Priority | Done | Notes
Ships |  | 1 | N
Stars |  | 2 | N

## FinalTesting
Phase 5 : Final Testing
Task | Subtask | Priority | Done | Notes
Game Loop |  | 1 | N | Does the game loop through its screens without bugs